## Summary (hidden)
Workflow Inventory — Summary
Use this sheet to track overall coverage progress. Update the count columns as inventory is completed.
Workflow Area | Total Workflows | Automate (new) | Migrate (existing) | Manual — defer | Out of scope
Connect Web | 10 | 6 | 2 | 1 | 1
Connect Mobile | 9 | 6 | 2 | 1 | 0
CommCare Mobile | 10 | 6 | 2 | 1 | 1
TOTAL | 29 | 18 | 6 | 3 | 2
How to use this template:
1. Start with the Summary sheet to understand the full scope at a glance.
2. Complete one row per workflow across the three tabs: Connect Web, Connect Mobile, CommCare Mobile.
4. For 'Automation Action' choose: Automate (new script), Migrate (existing script), Manual — defer, or Manual — out of scope.
5. The Notes column is especially important for CommCare — flag any workflows that may need CommCare developer input.
6. Once complete, the prioritised automation backlog is all rows marked Automate or Migrate, sorted by Release Risk (High first).

## Connect Web
Workflow Inventory — Connect Web ¦ Framework: Playwright
Priority | Workflow Name | Release Type (every release / regression / ad-hoc) | Release Risk (High / Medium / Low) | Existing Script? (yes / no) | Current Automation Status (yes / no) | Existing Script Name (if yes) | Flakiness (High / Medium / Low / N/A) | Automation Action | Notes / Dependencies ( blocker? volatile?)
1 | Program Creation |  | High | Yes | Yes |  |  | Migrate — existing script
2 | Programs List Page |  | Medium
3 | Opportunity Creation |  | High | Yes | Yes |  |  | Migrate — existing script
4 | Opportunity List page |  | Medium
5 | Opportunity Dashboard |  | High | Yes |  |  |  | Automate — new script
6 | Connect Workers Page |  | Medium |  |  |  |  | Migrate — existing script
12 | Visit Verification Page |  | High |  |  |  |  | Automate — new script
13 | Invoice List Page |  | Medium |  |  |  |  | Automate — new script
14 | Conect Messaging |  | Medium |  |  |  |  | Automate — new script
15 | Re-Learn Tasks |  | High |  |  |  |  | Automate — new script
16 | Microplanning |  | High |  |  |  |  | Automate — new script
17 | Solicitations |  | Low |  |  |  |  | Automate — new script
18
19
20
21

## Connect Mobile
Workflow Inventory — Connect Mobile ¦ Framework: Maestro
Priority | Workflow Name | Release Type (every release / regression / ad-hoc) | Priority | Release Risk (High / Medium / Low) | Existing Script? (yes / no) | Current Automation Status (yes / no) | Existing Script Name (if yes) | Flakiness (High / Medium / Low / N/A) | Automation Action | Notes / Dependencies (blocker? volatile?)
1 | PersonalID Signup | Every release | High |  | No
2 | PersonalID Recovery | Every release | High |  | Yes | Yes
3 | Connect Landing Page/ Opportunity List Page (Wait) | Every release | Medium |  | No
4 | Connect Integrations Tests (LDVP) (Wait) | Every release | High
5 | Connect Messaging | Every release | Low
6 | Connect Notifications | Every release | Medium |  | Yes
7 | Case List Map | Every release | Medium |  | No
8 | Connect Work History | Every release | Low |  | No
9 | Traditional App Install & Login | Every release | Medium
10 | Manage Profile (Future feature)
11 | Email Addition (After 2.64 release)
12 | Learning Tasks (Wait)
13
14
15
16
17
18
19

## CommCare Mobile
Workflow Inventory — CommCare Mobile ¦ Framework: Maestro
1. [Master] Mobile Plan (2026) 2. Existing Unit Tests coverage
Priority | Workflow Name | Release Type (every release / regression / ad-hoc) | Release Risk (High / Medium / Low) | Existing Script? (yes / no) | Existing Script Name (if yes) | Flakiness (High / Medium / Low / N/A) | Automation Action | Notes / Dependencies (CommCare dev needed? blocker? volatile?) | Maestro Automated (Yes / Partial Coverage / No / N/A) | Tests Automated (Count) | Not Automatable (Count)
1 | Browserstack/Android Virtual Devices |  | High | No |  |  | Manual — out of scope | AV: This is to ensure that CommCare still runs in the min supported version. BrowserStack automated tests only offer devices running Andorid 8.1+. So I believe this will still need to be done manually. | N/A - manual, out of scope for Maestro | 0 | 35
2 | Install |  | High | Partial Coverage |  |  |  | InstallFromListTest automates the "See Apps for My User" install path for both mobile and web workers (Install 4–8 in the workbook), and BaseTest installs apps from CCZ. The barcode-scan install flow (Install 1) is not automated. | Yes | 7 | 0
3 | Login |  | High | Yes |  |  |  |  | Yes | 3 | 0
4 | Update |  | High | Partial Coverage |  |  |  | Update behavior is touched indirectly: LanguagesTest.testAppUpdate_dontInterfereLanguageChanges, DemoUser*Test.testPracticeMode_withUpdatedApp, DeveloperOptionsTests.testUpdateOptions, and AppPreferenceSettingsTest.testUpdateFrequencySetting. | Partial Coverage (9/14) | 9 | 3
5 | Mobile Pins |  | High | No |  |  |  |  | Partial Coverage (21/22) | 21 | 1
6 | Multimedia |  | High | Partial Coverage |  |  |  | only slices are automated: MediaEncryptionTest (image/audio encryption), FormAttachmentUploadTest/FormAttachmentLimitTest, SignatureTests. Capture/playback across media types remains manual. | Partial Coverage (55/66) | 55 | 11
7 | Support Menus |  | High | Yes |  |  |  |  | Yes | 2 | 0
8 | Case Filters |  | High | Yes |  |  |  |  | Partial Coverage (10/13) | 10 | 3
9 | Session Expiration |  | High | Yes |  |  |  |  | Yes | 2 | 0
10 | Conditional Enum in Case List |  | High | Yes |  |  |  |  | Partial Coverage (6/8) | 6 | 2
11 | Prompt Updates |  | High | Partial Coverage |  |  |  |  | Partial Coverage (11/13) | 11 | 2
12 | Menu Badges |  | High | Yes |  |  |  |  | Partial Coverage (4/5) | 4 | 1
13 | Date Widgets |  | High | Yes |  |  |  |  | Yes | 5 | 0
14 | Other - Error Tests |  | High | Yes |  |  |  |  | Partial Coverage (7/11) | 7 | 4
15 | External App Tests |  | High | Partial Coverage |  |  |  | FixturesTest covers the external-app fixture side (missing fixture errors, filtering, 1MB fixture), but not the full external-app callout scenarios in the tab. | Partial Coverage (8/9) | 8 | 1
16 | Right to Left Text |  | High | No |  |  |  |  | Partial Coverage (10/26) | 10 | 18
17 | Update (partial and failed) |  | High | No |  |  |  |  | Partial Coverage (27/29) | 27 | 2
18 | Recovery Measures |  | High | Partial Coverage |  |  |  | SyncRecoveryTest (recovery sync) and AsyncRestoreTest (restore on login/sync) cover data-recovery paths. UPDATE (2026-08-26): the tab's forced app-update/reinstall recovery flows ARE NOW automated - a new Appium-based module (scripts/appium_offline_ccz_scenarios.py + scripts/run_appium_offline_ccz_suite.py) pushes a real .ccz file onto the device via BrowserStack push_file (Maestro itself has no file-push mechanism), confirmed passing live in CI (run 32936440687). The CC Reinstall/Update Needed client-swap limitation is also resolved (whole-session-on-old-client dispatch, not a mid-session swap). One exception: Retry Recovery 2 (network-toggle retry-button test) is Not Automatable - its measure is version-gated to CommCare client 2.45-2.54 only (confirmed via the app's own Django admin record), so it can't fire against the current release client under test regardless of automation approach. See docs/[Master] Mobile Plan (2026).xlsx Recovery Measures tab for the row-level detail. | Partial Coverage (43/47) | 43 | 4
19 | Form Submissions |  | High | Yes |  |  |  |  | Partial Coverage (36/51) | 36 | 15
20 | Trigger Device Logs |  | High | Partial Coverage |  |  |  | LogSubmissionTest covers log submission and "Report Problem", but not the HQ-initiated "request device logs" flow specifically. | Partial Coverage (3/4) | 3 | 1
21 | Updates |  | High | Partial Coverage |  |  |  | Setup 2, Prompted Update Scenario 1 (optional CommCare APK prompt), and Prompted Update Scenario 2 (forced CommCare APK blocker, currently failing on-device - open investigation) are automated via scripts/run_suite.py + hq_setup/updates_2_49/*.json, with apk_version resolved dynamically against whichever HQ option is labeled "(dev)" (never hardcoded). Auto CC Update 1/3 and Rate Limit 1 are also automated. In-App Update 1-10 (real Play Store) and Scenario 3 (timed manual wait) remain not automatable. | Partial Coverage (10/24) | 10 | 14
| TOTAL | [8 empty] | 279 | 82 | 77.3% automated (279/361 test cases) - excludes Browserstack/Android Virtual Devices (35 test cases, already marked Not automatable/out of scope for Maestro)

## CommCare Mobile - Non-Core
Workflow Inventory – CommCare Mobile - Non-Core ¦ Framework: N/A (outside Maestro automation program)
1. [Master] Mobile Plan (2026) - the 15 tabs not listed on the "CommCare Mobile" tab. 2. Re-reviewed row by row on 2026-10-02 against the test steps, commcare-android source and the HQ apps themselves; several earlier notes were corrected (see each row). Automation for these tabs lives in flows_non_core/ and runs from its own workflow, .github/workflows/maestro-browserstack-non-core.yml - separate from the core flows/ suite. 3. 'Tests Automated' counts only sheet rows covered by flows that passed a live BrowserStack run. 'Automatable - not yet automated' is the rest of what the review found automatable. 4. Row-level status is also in each of these 15 Master Plan tabs, columns I/J/K (Maestro Automatability / Automated? / Flow File) - the same columns the core tabs use. Second re-scan 2026-10-02 added Graphing 6-12/18, Print from Detail 3, Database Change 10-12, Custom Properties 1, Third Party Scanner 2/6 and Personal ID TC_04. 5. Open questions answered 2026-10-23: Print from Detail is deprecated (rows N/A, flows removed); Mapbox 2 N/A; Personal ID TC_01-03 (no test OTP number) and TC_37-42 (fingerprint) not automatable; Graphing 20/22 are an HQ app configuration issue (flow kept, blocked until the app is fixed); Custom Properties 15: removed in 2.65 for good (mobile dev, 2026-10-27) - kept for 2.64 and earlier only. 6. 2026-10-23: the targeted-updates and CommCare-upgrade runners passed live and now run in the non-core CI workflow; Database 6 and Database Change 13 were automated (partial). 7. 2026-10-27: Graphing 20/22 automated on a fixed copy of the Graphing app (see the Graphing row).
Priority | Workflow Name | Release Type (every release / regression / ad-hoc) | Release Risk (High / Medium / Low) | Existing Script? (yes / no) | Existing Script Name (if yes) | Flakiness (High / Medium / Low / N/A) | Automation Action | Notes / Dependencies (CommCare dev needed? blocker? volatile?) | Maestro Automated (Yes / Partial Coverage / No / N/A) | Tests Automated (Count) | Not Automatable (Count) | Automatable - not yet automated (Count) | Test Cases (Count)
1 | Database Change |  | Medium | Yes | flows_non_core/database_change/ |  |  | Automated in flows_non_core/database_change/ (passed live): Setup 2-3 and Database Change 10-12 - install the second most recent Basic Tests build (pinned v1139), update it to the current one, then App Manager > Advanced > Data Change Logs shows 'CommCare installed', 'App installed' and 'App updated' (messages from commcare-android DataChangeLog.kt). Database 6 (partial): the Multimedia Only form with a gallery image and video, submitted, then reopened from Saved still lists both files (audio has no fixture; signature/acquire-only tiles need a companion app). Database Change 13 (partial): Data Change Logs > Share > Gmail opens Gmail - BrowserStack's devices have no Google account, so the draft/attachment and sending (steps 4-7) stay manual. Setup 1, Database 2, Final 1-2 and Database 7/9 (passed live 2026-10-23, 2.45 -> 2.65.0): scripts/run_appium_non_core_upgrade_suite.py --scenario database_change_upgrade installs CommCare 2.45 (resources/commcare_2.45_release.apk) with the 'Database Change!' app, saves an incomplete form, upgrades CommCare to the release mid-session (BrowserStack Appium), then checks the form survived and Data Change Logs shows 'CommCare updated'; runs in the non-core workflow's group-b. Not automatable: Setup 4 / Final 3 (airplane mode - network toggling on BrowserStack is a confirmed dead end) and therefore Database 1, 3, 4, 5 and Final 4 (without going offline the forms just submit); Database 8 needs Android 8 or lower (BrowserStack's minimum is 8.1). | Yes | 13 | 8 | 0 | 21
2 | SD Card Dump |  | N/A | Yes | flows_non_core/sd_card_dump/ |  |  | Needs two phones with SD card slots and physically moving the card - out of scope. Exception, automated in flows_non_core/sd_card_dump/: SD Card 1 (Advanced > Manage SD shows the 'Form Dump' warning, then the Dump/Submit screen) - single-device, passed live. | Yes | 1 | 15 | 0 | 16
3 | Wi-Fi Direct |  | N/A | Yes | flows_non_core/wifi_direct/ |  |  | Needs two devices peer-connected over Wi-Fi Direct - out of scope. Exception, automated in flows_non_core/wifi_direct/: WiFi 1 (Advanced > Wi-Fi Direct opens the Send/Receive/Submit dialog and switches mode) - single-device, passed live. | Yes | 2 | 7 | 0 | 9
4 | Developer Options |  | Low | Yes | flows_non_core/developer_options/ |  |  | Automated in flows_non_core/developer_options/: do_01 (Setup 1-2 + DO1, all four option items), do_03 / do_04 (image above / below the question label, checked with Maestro's above/below position matchers - the same isAbove/isBelow checks commcare-android's DeveloperOptionsTests.kt makes). DO2 only says 'run the Update tab' - covered there, counted N/A here. | Yes | 5 | 0 | 0 | 6
5 | Printing |  | Medium | Yes | flows_non_core/printing/ |  |  | Automated in flows_non_core/printing/ (all passed live): Form Printing 1-4 (fill Name/Age/Hometown, Get Data, Android's print UI opens). Print from Detail 1-4 are N/A: printing from the case detail is deprecated (confirmed with the team 2026-10-23), so the Print from Detail flows and the pinned v1133 build they used were removed from the suite. Not automatable: Form Printing 5 (checking the PDF's contents). | Yes | 4 | 1 | 0 | 9
6 | Graphing |  | Medium | Yes | flows_non_core/graphing/ |  |  | Correction to the earlier note: graphs are NOT custom-drawn canvas - commcare-android renders them as c3/d3 SVG in a WebView (app/src/org/commcare/graph/view/GraphView.java), and Maestro can read their text (proven live). Automated in flows_non_core/graphing/ (passed live): Graphing 1-5, End Form 1, 19 (create case, add a point, view it, remove it - cleans up after itself), 6 (axis titles, tick labels zero/five/ten, BOTTOM, Secondary Y Values), 7-11 (each graph tab's titles/annotations: TOP, DateTime, JUNE, Fill Graph, Number One/Two, number2, Bar Horizontal Graph), 12 (double-tap opens the XY and Fill graphs full screen) and 18 (Remove a Point list with X/Y/Radius columns). Graphing 20/22 (passed live 2026-10-27) run on 'Graphing - Maestro Reports [DO NOT DELETE]', a copy of the Graphing app made for automation: the original's two report graphs have custom series data paths on the removed v1 report fixture (instance('reports') = jr://fixture/commcare:reports, hence 'Unable to find lookup table') and v1 column syntax; the copy uses the v2 fixtures (instance('commcare-reports:<report_slug>')/rows/row, x/y column_0..2). The original app is unchanged - manual testers on it still hit the error until the same two edits are made there. Not automatable: Graphing 13-17 and 21 (tap an individual data point - its screen position depends on device and data); colours, zoom/drag quality and rotation distortion in 6-12 stay visual. | Yes | 17 | 6 | 0 | 23
7 | NFC |  | N/A | No |  |  |  | Not automatable (16 test rows - the earlier count of 14 was wrong): only runs on the NFC-capable tablet in the Dimagi office, tapped against a physical NFC bracelet. No cloud device offers this. | N/A - not automatable | 0 | 16 | 0 | 16
8 | Auto Form Submission |  | N/A | No |  |  |  | Not automatable: needs airplane-mode/network toggling (a confirmed BrowserStack dead end), a low-battery device state, and an hour-plus unattended wait. | N/A - not automatable | 0 | 6 | 0 | 6
9 | Mapbox |  | Medium | Yes | flows_non_core/mapbox/ |  |  | Automated in flows_non_core/mapbox/ (all passed live): Mapbox 1 (GPS Normal capture), 4 (location permission denied via Maestro's launchApp permissions - CommCare re-asks and the capture completes once allowed) and 5 (new case in the Followup case list); the appearance='maps' question is captured too. Mapbox 2 is N/A (confirmed 2026-10-23): commcare-android removed Mapbox in 2.59.0 (commits 4607202fb / e6d3972c6), so 'maps' questions now open the Google-map picker. Mapbox 3 (turn device GPS off system-wide) is not automatable. | Yes | 3 | 1 | 0 | 5
10 | Text to Speech |  | Medium | Yes | flows_non_core/text_to_speech/ |  |  | Automated (partial) in flows_non_core/text_to_speech/ (all passed live): TTS 1-2 (enable the setting; audio button shows and can be tapped), TTS 3 (form language switched to Hindi - label changes, button stays), TTS 4 (app language switched to Hindi, same check). We can't check that speech actually plays or is in Hindi. TTS 5-6 need on-device language packs downloaded/deleted through the OEM TTS engine settings - not reliable across BrowserStack devices. | Yes | 4 | 2 | 0 | 6
11 | Third Party Scanner |  | N/A | Yes | flows_non_core/third_party_scanner/ |  |  | Rows 1, 3-5 and 7 need a third-party scanner app installed from the Play Store (no internal APK) - not automatable. Automated in flows_non_core/third_party_scanner/ (passed live): row 2 (toggle 'Use intent callout for scanner') and row 6 (with it disabled, the barcode question's Get Barcode opens CommCare's built-in scanner). With no third-party app installed CommCare falls back to the built-in ZXing scanner either way (WidgetUtils.createScanIntent), so the flow checks the setting and that the scanner launches, not which one. | Yes | 2 | 5 | 0 | 7
12 | Advanced Settings |  | Low | Yes | flows_non_core/advanced_settings/ |  |  | Automated in flows_non_core/advanced_settings/ against the 'Advanced Settings' app (its custom properties are already set on HQ - nothing is changed there), all passed live: Custom Properties 1 (PIN offer, don't-ask-again, Set My PIN, PIN login), 2, 4, 5, 6, 7, 8, 9, 10, 15 and Settings 1, 4. Custom Properties 15 applies to CommCare 2.64 and earlier only: 2.65 deleted root-menu-as-home-screen (commcare-android 568e15b6d), so the flow is tagged commcare_max_2_64 and reported as skipped, with the reason, on 2.65+ APKs. The mobile dev confirmed 2026-10-27 that the feature is gone for good (no replacement), so the row and flow can be retired once 2.64 is no longer tested. Custom Properties 11-14 (cc-update-target release/build/save and pre-update-sync-needed, passed live 2026-10-23 on 2.65.0) run through scripts/run_targeted_updates_check.py, which sets the Targeted Updates App's custom properties on HQ, cuts the builds each row needs, runs the flow and restores the app's original settings + a clean released build afterwards; it runs in the non-core workflow's group-a. Not automatable: Custom Properties 3, Settings 2, Settings 3 (they change the device clock/date) and Custom Properties 16 (its check is that captured media files on the device end in .aes - listing app files needs adb_shell, which BrowserStack disables). | Yes | 16 | 4 | 0 | 20
13 | Performance Tests |  | Low | Yes | flows_non_core/performance_tests/ |  |  | Automated in flows_non_core/performance_tests/ (passed live): the two timing rows on Large App as the sheet's 'large' user - first run (2026-10-02, Galaxy S26 / Android 16): cold start to login screen 3.6 s, login to home screen ~114 s (includes the initial data restore). Times are reported on each CI run's summary page (scripts/extract_flow_timings.py); the budgets are loud-failure ceilings until real limits are agreed. Perf 1-2 (passed live 2026-10-23): scripts/run_appium_non_core_upgrade_suite.py --scenario performance_upgrade - CommCare 2.45 + Large App v194, upgraded mid-session to 2.65.0, then both timings on the upgraded client: cold start 2.0 s, login 57.8 s. Runs in the non-core workflow's group-b. | Yes | 4 | 0 | 0 | 4
14 | Case List Optimization and Cach |  | Medium | Yes | flows_non_core/case_list_optimization/ |  |  | Automated in flows_non_core/case_list_optimization/ (all passed live): Setup 1-2, Cache and index-1/2 (lists load; sort-order check not done yet) and Load time-1..8, each timed in code with a loud-failure ceiling (60 s) until real limits are agreed. Times appear on each CI run's summary page (scripts/extract_flow_timings.py) - first live run: Load time-1 3.1 s, Cache and index-1 3.0 s, -2 2.9 s. Correction to the earlier note: Load time-6 (clear app data) and -7 (force stop) are NOT blocked - those limits were Appium's; Maestro's own clearState and stopApp both work on BrowserStack (passed live). Exploratory testing stays manual. Runs as the sheet's '123' user (CC_CASELIST_USERNAME/PASSWORD). | Yes | 13 | 1 | 0 | 14
15 | Personal ID |  | N/A | Yes | flows_non_core/personal_id/ |  |  | Mostly the Connect/PersonalID product, not CommCare Mobile. Automated in flows_non_core/personal_id/ (passed live): TC_04 - 'Sign up for PersonalID' is offered in the login screen's menu (shown when nobody is signed in and the device passes PersonalID's compatibility check; it does on BrowserStack's Galaxy S26). TC_43-46 are HQ web checks (mobile workers page) - N/A for this mobile suite. The rest are not automatable, confirmed with the team 2026-10-23: TC_01-03 need an SMS OTP and there is no test number that receives one; TC_37-42 need fingerprint enrollment. | Yes | 1 | 46 | 0 | 47
| TOTAL | [6 empty] | 85 of 209 test cases automated so far; 0 more assessed automatable; 118 not automatable; the rest N/A. |  | 85 | 118 | 0 | 209